## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want secure signup and login so that my project data is associated with my account. | MUST HAVE | FastAPI and bcrypt | Param Kumar | 3- Completed
Sprint 1 | Sprint 1 | US-02 | As a user, I want my uploaded-document history to load after login so that I can continue previous analysis. | MUST HAVE | US-01 and local JSON storage | Param Kumar | 3- Completed
Sprint 1 | Sprint 1 | US-03 | As a user, I want to upload PDF, DOCX, CSV, and TXT files so that different project records can be analyzed. | MUST HAVE | Document loaders | Param Kumar | 3- Completed
Sprint 1 | Sprint 1 | US-04 | As a user, I want empty, unsupported, corrupted, and oversized files handled clearly so that failed uploads are understandable. | MUST HAVE | US-03 | Param Kumar | 3- Completed
Sprint 1 | Sprint 1 | US-05 | As a system, I want project text split into overlapping chunks so that retrieval keeps useful context. | MUST HAVE | US-03 | Param Kumar | 3- Completed
Sprint 1 | Sprint 1 | US-06 | As a system, I want Gemini embeddings stored in ChromaDB so that project knowledge can be searched semantically. | MUST HAVE | US-05 and Gemini API | Param Kumar | 3- Completed
Sprint 1 | Sprint 1 | US-07 | As a system, I want large CSV files grouped into 40-row chunks so that indexing stays within token limits. | SHOULD HAVE | US-03 | Param Kumar | 3- Completed
Sprint 1 | Sprint 1 | US-08 | As a user, I want rate-limit retries and clear 429 messages so that temporary Gemini limits do not silently fail. | SHOULD HAVE | US-06 and Gemini API | Param Kumar | 3- Completed
Sprint 1 | Sprint 1 | US-09 | As a user, I want a dashboard showing documents, average health, and risk counts so that project status is visible quickly. | MUST HAVE | US-02 and analysis results | Param Kumar | 3- Completed
Sprint 2 | Sprint 2 | US-10 | As a project manager, I want an AI-generated health score, scope summary, risks, recommendations, and user stories. | MUST HAVE | US-06 | Param Kumar | 3- Completed
Sprint 2 | Sprint 2 | US-11 | As a reviewer, I want every identified risk supported by document evidence so that conclusions are traceable. | MUST HAVE | US-10 | Param Kumar | 3- Completed
Sprint 2 | Sprint 2 | US-12 | As a reviewer, I want the health-score methodology explained so that I understand which project factors affected the score. | MUST HAVE | US-10 | Param Kumar | 3- Completed
Sprint 2 | Sprint 2 | US-13 | As a user, I want delivery forecasting with delay risk, basis, blockers, and actions so that schedule issues can be addressed early. | MUST HAVE | US-06 | Param Kumar | 3- Completed
Sprint 2 | Sprint 2 | US-14 | As a user, I want to ask difficult project questions and receive answers grounded only in uploaded documents with source names. | MUST HAVE | US-06 | Param Kumar | 3- Completed
Sprint 2 | Sprint 2 | US-15 | As a user, I want readable chat answers with headings, bullets, emphasis, and copy support so that responses are easy to use. | SHOULD HAVE | US-14 | Param Kumar | 3- Completed
Sprint 2 | Sprint 2 | US-16 | As a user, I want to preview PDF, DOCX, CSV, and TXT files before upload so that I can verify the selected document. | SHOULD HAVE | Browser File API and Mammoth | Param Kumar | 3- Completed
Sprint 2 | Sprint 2 | US-17 | As a user, I want risks grouped by document and filterable by severity so that critical issues are prioritized. | SHOULD HAVE | US-10 | Param Kumar | 3- Completed
Sprint 2 | Sprint 2 | US-18 | As a user, I want Word and PDF health reports so that analysis can be shared outside the platform. | MUST HAVE | US-10 | Param Kumar | 3- Completed
Sprint 2 | Sprint 2 | US-19 | As a user, I want dark and light themes, loading states, and friendly errors so that the application feels reliable. | SHOULD HAVE | Core frontend flows | Param Kumar | 3- Completed
Sprint 2 | Sprint 2 | US-20 | As a reviewer, I want a mentor presentation and structured internship artifacts so that the solution can be evaluated clearly. | SHOULD HAVE | Completed project features | Param Kumar | 3- Completed
Sprint 3 | Sprint 3 | US-21 | As a user, I want to connect Gmail and select project-related emails for secure ingestion into the project knowledge base. | SHOULD HAVE | Google OAuth consent and Gmail API | Param Kumar | 2- In Progress
Sprint 3 | Sprint 3 | US-22 | As a mobile user, I want complete phone and tablet responsiveness so that every workflow is usable on smaller screens. | COULD HAVE | Responsive UI review | Param Kumar | 2- In Progress
Sprint 3 | Sprint 3 | US-23 | As a maintainer, I want automated backend and frontend regression tests so that future changes are safer. | SHOULD HAVE | Stable API contracts | Param Kumar | 2- In Progress
Backlog |  | US-24 | As a stakeholder, I want containerized cloud deployment so that the platform can be demonstrated without local setup. | COULD HAVE | Docker and cloud account | Param Kumar | 1- Not Started

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 162 | 9 | 14 | 13 | 12 | 13 | 11 | 11 | 15 | 11 | 11 | 12 | 10 | 14 | 6
SPRINT 1 BACKLOG
US-01 | T-01 | Create backend and frontend project structure | 2026-08-24 | 2026-08-24 | Param Kumar | Build | 3- Completed | 4 | Day 1: 4
US-01 | T-02 | Configure FastAPI, CORS, environment loading, and health route | 2026-08-24 | 2026-08-24 | Param Kumar | Coding | 3- Completed | 5 | Day 1: 5
US-01 | T-03 | Implement bcrypt signup and login endpoints | 2026-08-25 | 2026-08-25 | Param Kumar | Coding | 3- Completed | 8 | Day 2: 8
US-02 | T-04 | Implement JSON user history persistence and owner filtering | 2026-08-25 | 2026-08-26 | Param Kumar | Coding | 3- Completed | 8 | Day 2: 3; Day 3: 5
US-03 | T-05 | Implement PDF, DOCX, CSV, and TXT document loaders | 2026-08-26 | 2026-08-27 | Param Kumar | Coding | 3- Completed | 10 | Day 3: 5; Day 4: 5
US-04 | T-06 | Add file validation and friendly upload errors | 2026-08-27 | 2026-08-27 | Param Kumar | Coding | 3- Completed | 5 | Day 4: 5
US-07 | T-07 | Implement 40-row CSV grouping and safe text splitting | 2026-08-27 | 2026-08-28 | Param Kumar | Coding | 3- Completed | 6 | Day 4: 2; Day 5: 4
US-05 | T-08 | Configure overlapping document chunking | 2026-08-28 | 2026-08-28 | Param Kumar | Coding | 3- Completed | 4 | Day 5: 4
US-06 | T-09 | Integrate Gemini embeddings and persistent ChromaDB | 2026-08-28 | 2026-08-31 | Param Kumar | Integration Test | 3- Completed | 10 | Day 5: 5; Day 6: 5
US-08 | T-10 | Add batched embeddings and exponential-backoff retry | 2026-08-31 | 2026-08-31 | Param Kumar | Coding | 3- Completed | 6 | Day 6: 6
US-10 | T-11 | Design structured analysis prompt and JSON parsing | 2026-09-01 | 2026-09-02 | Param Kumar | Design | 3- Completed | 10 | Day 7: 5; Day 8: 5
US-11 | T-12 | Add risk severity, category, and document evidence | 2026-09-02 | 2026-09-02 | Param Kumar | Coding | 3- Completed | 6 | Day 8: 6
US-12 | T-13 | Add health-score methodology and summary | 2026-09-02 | 2026-09-02 | Param Kumar | Coding | 3- Completed | 4 | Day 8: 4
US-13 | T-14 | Implement delivery forecast, basis, blockers, and actions | 2026-09-03 | 2026-09-03 | Param Kumar | Coding | 3- Completed | 8 | Day 9: 8
US-14 | T-15 | Implement grounded query endpoint with source filtering | 2026-09-03 | 2026-09-04 | Param Kumar | Coding | 3- Completed | 8 | Day 9: 3; Day 10: 5
US-18 | T-16 | Generate structured Word health report | 2026-09-04 | 2026-09-04 | Param Kumar | Coding | 3- Completed | 6 | Day 10: 6
US-18 | T-17 | Generate styled PDF report with risk register | 2026-09-07 | 2026-09-07 | Param Kumar | Coding | 3- Completed | 8 | Day 11: 8
US-09 | T-18 | Build React authentication, sidebar, and dashboard | 2026-08-25 | 2026-09-01 | Param Kumar | Coding | 3- Completed | 12 | Day 2: 3; Day 3: 3; Day 7: 6
US-16 | T-19 | Build drag-and-drop upload and pre-upload preview | 2026-09-07 | 2026-09-08 | Param Kumar | Coding | 3- Completed | 10 | Day 11: 4; Day 12: 6
US-17 | T-20 | Build analysis, risks, and forecast views | 2026-09-08 | 2026-09-09 | Param Kumar | Coding | 3- Completed | 10 | Day 12: 4; Day 13: 6
US-15 | T-21 | Improve chat formatting, citations, copy action, and scrolling | 2026-09-09 | 2026-09-09 | Param Kumar | Coding | 3- Completed | 6 | Day 13: 6
US-19 | T-22 | Run build, lint, syntax, and manual workflow checks | 2026-09-09 | 2026-09-10 | Param Kumar | System Test | 3- Completed | 8 | Day 13: 2; Day 14: 6

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Backend and frontend dependencies required compatible isolated environments. | Created a Python virtual environment and installed frontend packages separately.
Sprint 1 | Day 2 | Authentication was needed without adding database setup complexity. | Used bcrypt password hashing with local JSON persistence for the internship demo.
Sprint 1 | Day 3 | Project documents arrived in multiple formats and structures. | Implemented format-specific loaders and normalized all content into LangChain documents.
Sprint 1 | Day 4 | Large CSV input could exceed prompt and embedding limits. | Grouped CSV data into 40-row chunks and applied safe secondary text splitting.
Sprint 2 | Day 1 | Gemini free-tier requests occasionally returned rate-limit errors. | Added batching, delay between embedding batches, exponential backoff, and clear 429 messages.
Sprint 2 | Day 2 | Initial risk results did not clearly show why a risk or score was assigned. | Added evidence for each risk plus methodology and forecast-basis sections.
Sprint 2 | Day 3 | AI answers and reports needed to be easier for reviewers to read and share. | Added structured chat rendering, copy support, and Word/PDF report exports.
Sprint 2 | Day 4 | File preview was available only after upload. | Added local pre-upload preview for PDF, DOCX, CSV, and TXT without sending the file to the backend.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-08-24 | 2026-09-04 | Param Kumar | Validate sample documents early and keep API responses structured. | Sending full large files to a single AI request. | Small integrations, source-controlled changes, and frequent build checks. | Introduced chunking, JSON response schemas, and retry handling.
2 | Sprint 2 | 2026-09-07 | 2026-09-18 | Param Kumar | Add evidence and test user-facing failure states before demo. | Showing unexplained AI scores or dense unformatted answers. | Keep clinician-style human review equivalent: AI drafts insights, user validates decisions. | Added evidence, methodology, formatted chat, previews, reports, and test artifacts.
3
4
5
6
7