## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Self Review | 2026-07-29 | Empty files could enter the upload flow and produce unclear processing errors. | Sprint 1 | Backend | Logical | Added an explicit empty-file check and returned HTTP 400 with a readable message. | 2026-07-30 | Closed | Verified with a zero-byte text file.
2 | Integration Test | 2026-07-31 | Large CSV content could create oversized chunks and increase token usage. | Sprint 1 | Backend | Maintainability | Grouped CSV records in batches of 40 rows and split only oversized groups. | 2026-08-03 | Closed | Chunk count returned by upload endpoint.
3 | Integration Test | 2026-08-04 | Gemini rate limits caused upload or analysis requests to fail immediately. | Sprint 1 | Backend | Logical | Added tenacity retry, exponential backoff, embedding batches, delays, and clear 429 responses. | 2026-08-06 | Closed | Failure remains visible after final retry.
4 | Analysis Review | 2026-08-10 | Risk cards did not show the document fact that supported each risk. | Sprint 2 | AI/Backend | Standards | Extended the analysis schema and prompt to return a specific evidence field for every risk. | 2026-08-11 | Closed | Evidence is shown beside severity and category.
5 | Analysis Review | 2026-08-12 | Health score and delay risk were difficult to defend during presentation. | Sprint 2 | AI/Backend | Standards | Added methodology for health scoring and a basis field for delivery forecasts. | 2026-08-14 | Closed | Explanations remain grounded in uploaded content.
6 | UI Review | 2026-08-17 | Long assistant answers appeared as dense plain text and were hard to scan. | Sprint 2 | Frontend | User Interface | Added safe structured rendering for headings, bullets, emphasis, paragraphs, and a copy-answer action. | 2026-08-19 | Closed | No raw HTML injection is used.
7 | UI Review | 2026-08-20 | Chat scrolled unnecessarily when switching document context or restoring messages. | Sprint 2 | Frontend | User Interface | Restricted smooth scrolling to newly appended messages. | 2026-08-21 | Closed | Document-specific chat history remains intact.
8 | UI Review | 2026-08-24 | Report buttons gave no feedback while Word or PDF generation was running. | Sprint 2 | Frontend | User Interface | Added separate export loading states and disabled repeat actions during generation. | 2026-08-26 | Closed | Both export flows show progress independently.
9 | User Workflow Test | 2026-08-28 | The document preview was available only after the upload action. | Sprint 2 | Frontend | User Interface | Added local preview before upload for PDF, DOCX, CSV, and TXT files. | 2026-08-31 | Closed | Preview does not send the file to the backend.
10 | Error Handling Test | 2026-09-01 | Corrupted or unsupported documents produced technical errors that were difficult to understand. | Sprint 2 | Full Stack | Logical | Mapped loader and API failures to visible document-level error messages. | 2026-09-03 | Closed | Other queued files continue processing.
11 | System Test | 2026-09-04 | Repeated analysis calls for the same document caused unnecessary AI requests. | Sprint 2 | Frontend | Maintainability | Cached analysis results by selected document and reused them during navigation. | 2026-09-07 | Closed | A separate cache entry is used for all-document analysis.
12 | Build Verification | 2026-09-09 | Frontend dependency changes required confirmation that the production bundle still compiled. | Sprint 2 | Frontend | Standards | Ran frontend build and lint checks and corrected integration issues before final packaging. | 2026-09-10 | Closed | Production build and static checks completed successfully.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others